## Slide 1
AMG ERP TRANSFORMATION
Modernising ERP while protecting operations, margins, and business continuity
Prepared for: AMG Executive Team
Focus: ERP replacement, scope control, and risk reduction
STRATEGY SLIDE DECK
2026 | ERP Transformation Strategy | Confidential

## Slide 2
EXECUTIVE SUMMARY: BUSINESS-LED TRANSFORMATION
Strategic Vision
AMG should approach the ERP replacement as a comprehensive business transformation, not just a technology upgrade. The goal is to align systems with operational excellence.
Controlled 12-month phased implementation focused on core stability.
Prioritize Day-1 processes: Finance, Procurement, Inventory, and Manufacturing.
Key Implementation Pillars
BOM/MRP Reliability: Ensuring data integrity from engineering to the shop floor.
Financial Visibility: Real-time margin tracking and cost control across all projects.
Operational Continuity: Minimizing disruption during cutover with rigorous testing.
Scope Discipline: Deferring non-critical automation and CRM/HRIS integration to Phase 2.
AMG ERP Transformation Strategy | Executive Summary
1

## Slide 3
CURRENT-STATE ANALYSIS: RISKS OF LEGACY SYSTEMS
OPERATIONAL FRAGILITY
Legacy ERP >20 years old; critical systems at end-of-life.
Fragile nightly sync between Engineering BOM and ERP.
Heavy reliance on Excel for reporting and workarounds.
FINANCIAL IMPACT
80%
of custom orders experienced margin erosion last year.
Weak visibility into project-level contribution margins.
Unreliable labor tracking affecting true cost calculations.
BUSINESS RISKS
BOM failures causing manufacturing delays and rework.
Siloed CRM and HRIS data preventing unified insights.
Operational delays impacting delivery and customer trust.
AMG ERP Transformation Strategy | Current-State Problem
2

## Slide 4
STRATEGIC PROGRAM OBJECTIVES & SUCCESS METRICS
Program Objectives
Protect Continuity: Ensure zero operational downtime during the ERP transition.
Modernize Core: Replace legacy systems with a scalable cloud-based ERP.
Data Governance: Establish "Single Source of Truth" for items, BOMs, and costs.
Margin Transparency: Real-time visibility into custom order and project profitability.
Process Efficiency: Eliminate manual Excel workarounds through automated reporting.
Measuring Success
AMG ERP Transformation Strategy | Program Objectives
Visibility
Instant access to order-level contribution margin reports.
Financial Control
Reliable and timely first month-end close in new system.
Data Integrity
100% accurate BOM and MRP processing post-launch.
Operational Stability
Stable go-live with no major business interruptions.
3

## Slide 5
RECOMMENDED 5-PHASE IMPLEMENTATION ROADMAP
PHASE 1
MOBILISE & ASSESS
Confirm scope & governance
Identify process owners
Risk & data assessment
PHASE 2
DESIGN FUTURE STATE
Standardize core processes
Engineering BOM integration
Reporting requirements
PHASE 3
BUILD & INTEGRATE
ERP configuration
Critical integrations
Data cleansing & migration
PHASE 4
TEST & PREPARE
User Acceptance Testing
Mock cutover simulations
Role-based training
PHASE 5
GO-LIVE & STABILISE
Controlled cutover
Hypercare support
Critical issue resolution
AMG ERP Transformation Strategy | 12-Month Phased Roadmap
4

## Slide 6
DAY-1 GO-LIVE SCOPE: CRITICAL OPERATIONS PRIORITY
Financials
General Ledger & Financial Close
Accounts Payable & Receivable
Fixed Assets & Tax Management
Supply Chain
Procurement & Purchase Orders
Inventory & Warehouse Management
Item Master & Costing
Operations
Manufacturing/MRP & Work Orders
Routing & Scheduling Basics
Sales Order Processing (Parts/Service)
Engineering
Engineering BOM Integration
ECN Process Controls
Controlled BOM Migration
Core Reporting
Financial Statements & Backlog
WIP & Order Margin Tracking
Inventory & Labour Cost Reports
Governance
Security Roles & User Access
Approval Workflows & Controls
Full Audit Trail Compliance
AMG ERP Transformation Strategy | Day-1 Go-Live Scope
5

## Slide 7
SCOPE DEFERRAL: STRATEGIC RISK REDUCTION
Strategic Deferral Logic
To control implementation risk, AMG must deliberately defer non-essential scope. This ensures the project team remains focused on the critical path to a stable go-live.
THE GUIDING RULE
"If it does not protect operations, financial close, compliance, BOM accuracy, or margin visibility, it should wait until Phase 2."
Deferred Items (Post-Stabilization)
Full CRM or HRIS/Payroll replacement.
Advanced AI analytics and forecasting.
Full historical transaction migration.
Complex custom workflows mimicking legacy systems.
Non-critical mobile apps and self-service portals.
Heavy customization without legal or operational mandate.
AMG ERP Transformation Strategy | Scope Deferral
6

## Slide 8
DATA MIGRATION & REPORTING STRATEGY
Data Migration Approach
Clean Master Data: Migrate customers, vendors, items, BOMs, and cost structures only after cleansing.
Open Balances: Focus on open orders, POs, inventory balances, and active projects.
Historical Archiving: Keep older transactions in a searchable reporting warehouse, not the new ERP.
Reporting & Validation
Transition Layer: Unified reporting access to both legacy and new ERP data during cutover.
Parallel Validation: Rigorous testing of financial reports against legacy outputs.
Mock Close: Perform at least one full month-end close simulation before final go-live.
AMG ERP Transformation Strategy | Data & Reporting
7

## Slide 9
TOP PROGRAM RISKS & MITIGATION STRATEGIES
KEY PROGRAM RISK
MITIGATION STRATEGY
Scope Creep & Complexity
Executive steering committee oversight.
Strict change control and Day-1 scope rules.
Poor Data Quality
Early data profiling and cleansing ownership.
Multiple mock migrations and business validation.
BOM/MRP Disruption
Prioritize BOM governance and ECN process design.
Engineering-manufacturing cross-validation.
Month-End Close Failure
Finance-specific testing and parallel reporting.
Full mock month-end close before final cutover.
User Adoption Failure
Role-based training and early process walkthroughs.
Super user network and hypercare support.
AMG ERP Transformation Strategy | Risk Management
8

## Slide 10
FINAL RECOMMENDATION & TARGET OUTCOMES
The Path Forward
AMG should proceed with a controlled 12-month cloud ERP transformation focused on operational stability, BOM accuracy, and financial control.
Standardize where possible; customize only where operationally essential.
Defer non-critical enhancements until after the stabilization phase.
Strategic Outcomes
Stable Day-1 Go-Live
Zero operational downtime and reliable business continuity.
AMG ERP Transformation Strategy | Final Recommendation
Margin Transparency
Real-time visibility into order-level contribution margins.
Financial Integrity
Reliable financial close and accurate master data governance.
Digital Foundation
A scalable platform for future automation and AI initiatives.
9

## Slide 11
SOURCES
Abouttmc.com (Data and Reporting Strategy)
NetSuite UK (Recommended Phasing Approach)
10

## Slide 12
THANK YOU